## Checklist
Data Cleaning & Readiness Checklist
Project Name: | Jeff's Project
Project Start Date: | 2026-02-21 | Total Tasks | Completed Tasks
Project End Date: | 2026-03-27 | 80 | 0 | 0%
Task Group | Task | Status | Priority | Due Date | Start Date | Complete Date | Comments
Intake & Context Validation | Business objective clearly defined (what decision will this data support) | FALSE | High | 2026-02-23
Intake & Context Validation | Key metrics and KPIs explicitly defined (formulas, grain, filters) | FALSE | High | 2026-02-23
Intake & Context Validation | Expected reporting level (daily, weekly, monthly, transactional) | FALSE | High | 2026-02-23
Intake & Context Validation | Known limitations or caveats shared by client | FALSE | High | 2026-02-23
Intake & Context Validation | Confirm how results will be consumed (dashboard, model, export, executive summary) | FALSE | High | 2026-02-23
Data Ownership & Governance | Data owner identified | FALSE | High | 2026-02-25
Data Ownership & Governance | Source system(s) documented | FALSE | High | 2026-02-25
Data Ownership & Governance | Refresh cadence confirmed (one-time vs recurring) | FALSE | High | 2026-02-25
Data Ownership & Governance | Historical backfill availability confirmed | FALSE | High | 2026-02-25
Data Ownership & Governance | Data privacy / PII considerations documented | FALSE | High | 2026-02-25
File & Structural Validation | File type confirmed (CSV, Excel, Parquet, database extract, API) | FALSE | Medium | 2026-02-27
File & Structural Validation | Encoding validated (UTF-8 preferred) | FALSE | Medium | 2026-02-27
File & Structural Validation | Consistent delimiter (CSV: comma vs pipe vs tab) | FALSE | Medium | 2026-02-27
File & Structural Validation | No merged cells(Excel) | FALSE | Medium | 2026-02-27
File & Structural Validation | Single header row only | FALSE | Medium | 2026-02-27
File & Structural Validation | No embedded totals or subtotals | FALSE | Medium | 2026-02-27
Table Structure | One table per file (no multiple layouts in one sheet) | FALSE | Medium | 2026-03-03
Table Structure | Column names are Unique, Descriptive, Free of spaces/special characters | FALSE | Medium | 2026-03-03
Table Structure | Column order consistent across files / extracts | FALSE | Medium | 2026-03-03
Table Structure | No duplicate columns with different names | FALSE | Medium | 2026-03-03
Data Types & Formatting | Numeric fields contain only numeric values | FALSE | Medium | 2026-03-05
Data Types & Formatting | Dates stored as dates (not text) | FALSE | Medium | 2026-03-05
Data Types & Formatting | Timestamps include time zone or are clearly defined | FALSE | Medium | 2026-03-05
Data Types & Formatting | Boolean fields standardized (0/1 or TRUE/FALSE) | FALSE | Medium | 2026-03-05
Data Types & Formatting | Categorical fields standardized (case, spelling) | FALSE | Medium | 2026-03-05
Data Types & Formatting | No mixed data types within a column | FALSE | Medium | 2026-03-05
Data Types & Formatting | No currency symbols in numeric fields | FALSE | Medium | 2026-03-05
Data Types & Formatting | Percentages stored as decimals or clearly labeled | FALSE | Medium | 2026-03-05
Data Types & Formatting | Leading/trailing whitespace removed | FALSE | Medium | 2026-03-05
Data Types & Formatting | Consistent decimal precision | FALSE | Medium | 2026-03-05
Grain & Uniqueness | Grain clearly defined (e.g. one row = one transaction per item per day) | FALSE | Low | 2026-03-09
Grain & Uniqueness | Grain matches analytical intent | FALSE | Low | 2026-03-09
Grain & Uniqueness | No hidden aggregation in source data | FALSE | Low | 2026-03-09
Grain & Uniqueness | Primary key identified | FALSE | Low | 2026-03-09
Grain & Uniqueness | Primary key uniqueness validated | FALSE | Low | 2026-03-09
Grain & Uniqueness | Composite keys documented (if applicable) | FALSE | Low | 2026-03-09
Grain & Uniqueness | Duplicate rows identified and resolved | FALSE | Low | 2026-03-09
Grain & Uniqueness | Surrogate key strategy defined (if needed) | FALSE | Low | 2026-03-09
Missing, Null, and Invalid Data | Null counts reviewed per column | FALSE | Low | 2026-03-11
Missing, Null, and Invalid Data | Expected vs unexpected nulls identified | FALSE | Low | 2026-03-11
Missing, Null, and Invalid Data | Business rules for null handling documented | FALSE | Low | 2026-03-11
Missing, Null, and Invalid Data | Decision per field: 1) Leave as NULL, 2) Default to 0, 3) Impute (mean/median/logic), 4) Exclude record | FALSE | Low | 2026-03-11
Missing, Null, and Invalid Data | Null handling consistent across layers (SQL, BI, models) | FALSE | Low | 2026-03-11
Missing, Null, and Invalid Data | Out-of-range values identified | FALSE | Low | 2026-03-11
Missing, Null, and Invalid Data | Negative values validated where applicable | FALSE | Low | 2026-03-11
Missing, Null, and Invalid Data | Sentinel values (-1, 999, "N/A") standardized or removed | FALSE | Low | 2026-03-11
Consistency & Referential Integrity | Totals equal sum of parts | FALSE | Low | 2026-03-13
Consistency & Referential Integrity | Dates align across related tables | FALSE | Low | 2026-03-13
Consistency & Referential Integrity | Status codes align with dates (e.g. closed date after open date) | FALSE | Low | 2026-03-13
Consistency & Referential Integrity | All foreign keys have matching parents | FALSE | Low | 2026-03-13
Consistency & Referential Integrity | Orphan records identified | FALSE | Low | 2026-03-13
Consistency & Referential Integrity | Lookup tables validated and deduplicated | FALSE | Low | 2026-03-13
Consistency & Referential Integrity | Many-to-many relationships explicitly modeled | FALSE | Low | 2026-03-13
Outliers & Distribution Review | Min / max reviewed | FALSE | Low | 2026-03-17
Outliers & Distribution Review | Distribution reviewed (skew, spikes) | FALSE | Low | 2026-03-17
Outliers & Distribution Review | Sudden step-changes flagged | FALSE | Low | 2026-03-17
Outliers & Distribution Review | Seasonality patterns validated (if applicable) | FALSE | Low | 2026-03-17
Outliers & Distribution Review | Outliers reviewed with stakeholder | FALSE | Low | 2026-03-17
Outliers & Distribution Review | Confirm whether outliers are: 1) Data errors, 2) Legitimate edge case, 3) One-time events | FALSE | Low | 2026-03-17
Time Series & Historical Integrity | Continuous date coverage validated | FALSE | Low | 2026-03-19
Time Series & Historical Integrity | Missing periods identified | FALSE | Low | 2026-03-19
Time Series & Historical Integrity | Backfilled data flagged | FALSE | Low | 2026-03-19
Time Series & Historical Integrity | Partial records labeled (YTD, MTD, WTD) | FALSE | Low | 2026-03-19
Time Series & Historical Integrity | Calendar vs fiscal logic documented | FALSE | Low | 2026-03-19
Time Series & Historical Integrity | Time zone consistency confirmed | FALSE | Low | 2026-03-19
Documentation & Transparency | Data Dictionary: Column name, Description, Data Type, Grain, Business rules, Source system | FALSE | Low | 2026-03-23
Documentation & Transparency | Cleaning assumptions documented | FALSE | Low | 2026-03-23
Documentation & Transparency | Know data issues logged | FALSE | Low | 2026-03-23
Documentation & Transparency | Tradeoffs explained | FALSE | Low | 2026-03-23
Documentation & Transparency | Client sign-off obtained | FALSE | Low | 2026-03-23
Readiness Gate (Go / No-Go) | Data quality issues reviewed with client | FALSE | Low | 2026-03-25
Readiness Gate (Go / No-Go) | All critical issues resolved or accepted | FALSE | Low | 2026-03-25
Readiness Gate (Go / No-Go) | Data deemed "fit for purpose" | FALSE | Low | 2026-03-25
Readiness Gate (Go / No-Go) | Version of source data locked | FALSE | Low | 2026-03-25
Readiness Gate (Go / No-Go) | Reproducible pipeline defined | FALSE | Low | 2026-03-25
Ongoing / Recurring Data Feeds | Automated schema checks | FALSE | Low | 2026-03-27
Ongoing / Recurring Data Feeds | Row count variance alerts | FALSE | Low | 2026-03-27
Ongoing / Recurring Data Feeds | Null rate monitoring | FALSE | Low | 2026-03-27
Ongoing / Recurring Data Feeds | Freshness checks | FALSE | Low | 2026-03-27
Ongoing / Recurring Data Feeds | Historical reconciliation | FALSE | Low | 2026-03-27
Formulas:
Completed Tasks = IFS(Tasks[[#This Row],[Status]],"Complete", Tasks[[#This Row],[Due Date]] - TODAY() <=7, "High", Tasks[[#This Row],[Due Date]] - TODAY() <=14, "Medium", TRUE, "Low")
Due Date = WORKDAY(B3, XLOOKUP(Tasks[[#This Row],[Task Group]], tblPlan[Task Group], tblPlan[Cumulative Days]) - 1, holiday[Holiday] )
Fields to edit:
1. Project Name
2. Project Start Date
3. Status (when complete)
4. Start Date, Complete Date, and Comments

## Definitions
Task | Definition | Example | Why it matters
Aggregation | Summarizing data using functions (i.e. SUM, COUNT, AVG, etc.) | Total sales by product | Produces meaningful metrics.
Anonymized Data | Data where personal identifiers have been removed or replaced with surrogate keys. | Replacing email with customer_id. | Protects privacy while allowing analysis.
Cardinality | The uniqueness of values in a column. | High cardinality: customer_id, Low cardinality: gender
Composite Key | A primary key made up of two or more columns that together uniquely identify a record. | (store_id, product_id, sale_date) | Used when no single column is sufficient to uniquely identify records.
Data Grain | The level of detail represented by each row in a table. | One row per card, one row per transaction. | Prevents aggregation errors.
Data Integrity | The accuracy, consistency, and reliability of data.
Data Type Validation | Ensuring each column uses the correct data type (i.e. integer, data, text, etc.) | price should be numeric, not text | Prevents calculation errors.
Data Validation | The process of ensuring data meets defined quality rules.
Deduplicated | Removing duplicate records so each key appears only once. | Ensuring each product_id appears only once in a lookup table. | Ensures accurate joins.
Dimension Table | A table containing descriptive attributes used to provide context for fact tables. | dim_product, dim_customer | Supports filtering, grouping, and reporting.
Fact Table | A table containing measurable business metrics. | fact_sales containing sales transactions | Stores the core data used for analysis.
Foreign Key | A column that references the primary key of another table to establish a relationship between tables. | fact_sales.product_id -> dim_product.product_id | Connects related data across tables.
Join | A SQL operation used to combine data from multiple tables based on matching keys. | Joining fact_sales to dim_product | Allows combining descriptive and transactional data.
Lookup Table | A table containing reference data used to provide additional information about keys. | dim_product containing product_names and categories | Provides descriptive attributes for analysis.
NULL Value | A value representing missing, unknown, or undefined data. | customer_email = NULL | May cause errors in joins and calculations.
Orphan record | A record in a child table whose foreign key does not exist in the parent table. | A sale referencing a product_id that does not exist in the product table. | Breaks relationships between tables and causes missing data in joins.
PII | Stands for Personally Identifiable Information. Any data that can identify a specific individual (i.e. name, email, phone number, address). | customer_name, email | Must be protected to ensure data privacy and regulatory compliance.
Primary Key | A column or set of columns that uniquely identifies each row in a table. | product_id | Ensures each record can be uniquely referenced.
Referential integrity | The condition where all foreign keys correctly reference existing primary keys in related tables. | Every product_id in fact_sales table exists in dim_product table. | Ensures consistency and valid relationships between tables.
Schema Validation | Ensuring table structure matches expected format and definitions. |  | Ensures consistency and compatibility.
Sentinal Value | A predefined placeholder value used instead of NULL to represent missing or unknown data. | product_id = -1 meaning "Unknown Product" | Allows joins to function correctly.
Surrogate Key | A system-generated unique identifier used as a primary key. It has no business meaning and exists solely to uniquely identify records. | product_id, customer_id, card_id | Provides stable, permanent identifiers that do not change if business data changes.
Unique Constraint | A rule ensuring all values in a column are unique

## Lookup
Holiday | Notes | Task Group | Block Days | Estimated Days | Cumulative Days
2026-01-01 | New Years Day | Intake & Context Validation | 5 | 2 | 2
2026-01-19 | MLK Day | Data Ownership & Governance | 5 | 2 | 4
2026-02-16 | Presidents' Day | File & Structural Validation | 6 | 2 | 6
2026-04-06 | Easter (Monday holiday) | Table Structure | 4 | 2 | 8
2026-05-25 | Memorial Day | Data Types & Formatting | 10 | 2 | 10
2026-06-19 | Juneteenth | Grain & Uniqueness | 8 | 2 | 12
2026-07-03 | Official holiday is Saturday, 7/4 | Missing, Null, and Invalid Data | 8 | 2 | 14
2026-09-07 | Labor Day | Consistency & Referential Integrity | 7 | 2 | 16
2026-10-12 | Columbus Day | Outliers & Distribution Review | 6 | 2 | 18
2026-11-26 | Thanskgiving | Time Series & Historical Integrity | 6 | 2 | 20
2026-11-27 | Day after Thanksgiving | Documentation & Transparency | 5 | 2 | 22
2026-12-24 | Christmas Eve | Readiness Gate (Go / No-Go) | 5 | 2 | 24
2026-12-25 | Christmas | Ongoing / Recurring Data Feeds | 5 | 2 | 26